| Title Programs |  |  |
| --- | --- | --- |
| Schoolwide Planning Timeline |  |  |
| - Local educational agency (LEA) establishes school eligibility | Prior to planning year |  |
| 2. LEA notifies school of eligibility | Spring prior to planning year |  |
| 3. School consults with stakeholders and makes | Prior to August 15 of the |  |
| decision to become schoolwide | planning year |  |
| 4. LEA sends Letter of Intent or Intent | By August 15 Prior to the planning year |  |
| Form to notify State educational agency (SEA) of plan to develop schoolwide |  |  |
|  Designates high quality technical | July-August planning year |  |
| assistance providers |  |  |
|  Identifies writing team | August of planning year |  |
| members |  |  |
|  Develops comprehensive needs | August-November of planning year |  |
| assessment |  |  |
| 5. LEA engages in planning and writing | November-March of planning year |  |
| process |  |  |
| 6. LEA sends draft of schoolwide plan to | April 30 of planning year |  |
| Title I Education Program Specialist |  |  |
| 7. Title I Education Program Specialist | May 30 of planning year |  |
| responds to LEA |  |  |
| 8. LEA submits edited/revised plan | June 30 of planning year |  |
| 9. SEA notifies LEA to include schoolwide | July 31 of implementation year |  |
| status in Consolidated Application |  |  |
| 10. SEA sends schoolwide program approval | August 1 of implementation year |  |
| letter from SEA |  |  |
| 11. School begins implementation of | August 1 |  |
| schoolwide |  |  |
| July 2012 |  |  |