|  |  | Local Staff Responsible | Timeline | Documentation | Date Completed |
| --- | --- | --- | --- | --- | --- |
|  | ID&R Planning and Implementation |  |  |  |  |
|  | Meet with ID&R staff to design a plan to complete the GaDOE MEP Re-sign process. | Local MEP Contact and Staff | 48 hrs after GaDOE Re-sign meeting | Agenda, sign-in, completed re-signs |  |
|  | Disseminate and train on all forms, travel logs, phone logs, weekly schedules, etc. that will be used by the MEP staff in the district to conduct ID&R. | Local MEP Contact and Staff | By August 31st | Agenda and sign-in |  |
|  | Meet with ID&R staff to brainstorm about recruitment needs, cases, and plan recruitment strategies based on the ID&R plan. | Local MEP Contact and Staff | Three times during school year and summer | Agenda and sign-in |  |
|  | Meet with ID&R staff to design the plan for review and follow up of the Occupational Survey that is completed during back-to-school and new student registration. | Local MEP Contact and Staff | By the end of the first week of school | Agenda and sign-in |  |
|  | Assign recruiters to recruitment areas making sure to account for year-round, ongoing recruitment efforts in the school district, community, fields, state and federal service agencies, congregation places, and include out-of-school-youth and pre-school aged children. | Local MEP Contact and Staff | By end of first school month and revisit quarterly | Assignment List |  |
|  | Contact current MEP eligible children and youth to determine if new qualifying moves have been made and complete COEs if needed. | Local MEP staff and GaDOE regional recruiters | During re-signs and on-going | Recruitment and Enrollment Reports |  |
|  | Contact potential MEP families and youth (based on Occupational Survey or other referrals) to determine eligibility. | Local MEP staff and GaDOE regional recruiters | Immediately and on-going | Completed COE, schedules, travel documents, etc. |  |
|  | Building the Local Recruitment Network |  |  |  |  |
|  | Review and update school district agricultural map. | Local MEP Contact and Staff | September 1st, January 1st, and June 1st | Completed and updated maps on file |  |
|  | Review and update the school district employer roster. | Local MEP Contact and Staff | September 1st, January 1st, and June 1st | Completed roster on file |  |
|  | Review and update the school district residential map to include areas, neighborhoods, and labor camps where migrant families reside. | Local MEP Contact and Staff | September 1st, January 1st, and June 1st | Completed map on file |  |
|  | Make assignments for contacting employers within the district regarding hiring practices, crops, and growing seasons. | Local MEP Contact and Staff | Review assignments on September 1st, January 1st, and June 1st | Assignment roster on file |  |
|  | Make assignments for ongoing contact and coordination with agencies that serve migrant families/OSYs/DOs to identify potential migrant children and youth. | Local MEP Contact and Staff | Review assignments on September 1st, January 1st, and June 1st | Assignment roster on file, calendars and schedules |  |
|  | ID&R Training |  |  |  |  |
|  | Notify GaDOE MEP regional office about newly hired staff | MEP Contact | By end of first week of employment | E-mail |  |
|  | View MEP video: Overview for New Employees and Contracted Personnel found on the GaDOE MEP website. | New hires | By end of first day of employment | Certificate from video |  |
|  | Attend New Hire ID&R Training offered by the state ID&R Coordinator or authorized regional recruiter(s). | All new hired staff (SSPs, Recruiters, MEP Contacts in LEAs without MEP funded staff) | By end of week four after hire date | Training agenda and sign-in |  |
|  | Attend all required GaDOE MEP ID&R Training. | All Georgia MEP personnel (SSPs, Recruiters, MEP Contacts in LEAs without MEP funded staff) | Dates are set during the school year | Training agenda and sign-in |  |
|  | Participate in Recruitment Observations Full-time staff in school districts without a full-time district recruiter will recruit with GaDOE regional recruiter once a quarter during the school year (three times a year). Full-time staff in school districts with a full time district recruiter will recruit with regional recruiter once a year. Part-time staff will recruit with regional recruiter once a year. | All Georgia MEP personnel | Quarterly or yearly | One or three recruitment observation forms per year |  |
|  | Novice level recruiter certification (completion of 10 COEs submitted and approved and other requirements). | All Georgia MEP personnel | No time limit to meet this requirement | Certificate of Completion |  |
|  | ID&R certification at the highest level offered by the state – Master level (completion of 200 COEs submitted and approved and other requirements). | All regional recruiters and full time district recruiters | No time limit to meet this requirement | Certificate of Completion |  |
|  | Georgia Agricultural Activities Map: http://batchgeo.com/map/6b7994570dec29184726c945215bef85 Updated 05/24/13 |

# Text boxes

Documentation of completion of these activities should be on the SSP/recruiter’s calendar and filed with the MEP contact (sign in sheets, agendas and/or forms).